## Sprint1
Current Sprint | 1
Sprint Duration (days) | 7
Start Date | 2022-07-25
End Date | 2022-07-31
Working Hours/day | 1
Calendar
|  | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31
| Chan Kei Yiu Yvone | [7 empty] | Available
| Hung-Wei Lin | [7 empty] | Not available
| Lai Yin Ping | [7 empty] | Not sure (count as 0.5)
Yusuf Fahry
Calculation
| Available slots | 17
| Uncertain slots | 3
| Projected capacity: | 66.0714 | %
| Story points completed last sprint |  | Projected story points
| - |  | 8

## Sprint2
Current Sprint | 2
Sprint Duration (days) | 7
Start Date | 2022-08-01
End Date | 2022-08-07
Working Hours/day | 1
Calendar
|  | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07
| Chan Kei Yiu Yvone | [7 empty] | Available
| Hung-Wei Lin | [7 empty] | Not available
| Lai Yin Ping | [7 empty] | Not sure (count as 0.5)
Yusuf Fahry
Calculation
| Available slots | 19
| Uncertain slots | 4
| Projected capacity: | 75 | %
| Story points completed last sprint |  | Projected story points
| 3 |  | 4

## Sprint3
Current Sprint | 3
Sprint Duration (days) | 7
Start Date | 2022-08-08
End Date | 2022-08-14
Working Hours/day | 1
Calendar
|  | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14
| Chan Kei Yiu Yvone | [7 empty] | Available
| Hung-Wei Lin | [7 empty] | Not available
| Lai Yin Ping | [7 empty] | Not sure (count as 0.5)
Yusuf Fahry
Calculation
| Available slots | 23
| Uncertain slots | 4
| Projected capacity: | 89.2857 | %
| Story points completed last sprint |  | Projected story points
| 5 |  | 7

## Sprint4
Current Sprint | 4
Sprint Duration (days) | 7
Start Date | 2022-08-15
End Date | 2022-08-21
Working Hours/day | 1.5
Calendar
|  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21
| Chan Kei Yiu Yvone | [7 empty] | Available
| Hung-Wei Lin | [7 empty] | Not available
| Lai Yin Ping | [7 empty] | Not sure (count as 0.5)
Yusuf Fahry
Calculation
| Available slots | 24
| Uncertain slots | 4
| Projected capacity: | 92.8571 | %
| Story points completed last sprint |  | Projected story points
| 8 |  | 12

## Sprint5
Current Sprint | 5
Sprint Duration (days) | 7
Start Date | 2022-08-22
End Date | 2022-08-28
Working Hours/day | 1
Calendar
|  | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28
| Chan Kei Yiu Yvone | [7 empty] | Available
| Hung-Wei Lin | [7 empty] | Not available
| Lai Yin Ping | [7 empty] | Not sure (count as 0.5)
Yusuf Fahry
Calculation
| Available slots | 23
| Uncertain slots | 3
| Projected capacity: | 87.5 | %
| Story points completed last sprint |  | Projected story points
| 11 |  | 7