## Initial Plan
TASK ID | TASK TITLE | DURATION IN DAYS | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
 | time axis 2022-06-13 to 2022-09-04
1 | Project Planning Phase
1.1 | Requirements collection | 7 | bar: 2022-07-04 to 2022-07-12
1.2 | project estimation | 5 | bar: 2022-07-08 to 2022-07-12
1.3 | Risk identification | 14 | bar: 2022-07-11 to 2022-07-24
1.4 | project charter | 14 | bar: 2022-07-11 to 2022-07-24
1.5 | risk register | 7
1.6 | communications plan | 7 | bar: 2022-07-04 to 2022-07-12
1.7 | confirmed requirements list | 7 | bar: 2022-07-11 to 2022-07-12; 2022-07-18 to 2022-07-24
1.8 | a scope baseline | 7 | bar: 2022-07-11 to 2022-07-12; 2022-07-18 to 2022-07-24
2 | Implementation phase
2.1 | Product design | 14 | bar: 2022-07-11 to 2022-07-12; 2022-07-25 to 2022-08-07
2.2 | Code development | 14 | bar: 2022-07-11 to 2022-07-12; 2022-07-25 to 2022-08-07
2.3 | Code demonstration | 14 | bar: 2022-07-11 to 2022-07-12; 2022-08-01 to 2022-08-14
2.4 | Customer feedback | 14 | bar: 2022-07-11 to 2022-07-12; 2022-08-01 to 2022-08-14
2.5 | Internal testing | 14 | bar: 2022-07-11 to 2022-07-12; 2022-08-01 to 2022-08-14
2.6 | Fix the bugs | 14 | bar: 2022-07-11 to 2022-07-12; 2022-08-01 to 2022-08-14
3 | Work the product toward the UAT
3.1 | Gantt chart | 7 | bar: 2022-07-11 to 2022-07-12; 2022-08-15 to 2022-08-21
3.2 | Review features | 7 | bar: 2022-07-11 to 2022-07-12; 2022-08-15 to 2022-08-21
3.3 | Test plan design | 7 | bar: 2022-07-11 to 2022-07-12; 2022-08-15 to 2022-08-21
3.4 | Prepare delivery package | 14 | bar: 2022-07-11 to 2022-07-12; 2022-08-15 to 2022-08-28
3.5 | Deliver the product | 7 | bar: 2022-07-11 to 2022-07-12

## Updated Plan
[44 empty] | Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3 | [6 empty] | Sprint 4 | [6 empty] | Sprint 5
TASK ID | TASK TITLE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26
 | time axis 2022-06-13 to 2022-12-11
1 | Project Planning Phase
1.1 | Requirements collection | bar: 2022-07-04 to 2022-07-10; 2022-08-07; 2022-08-22 to 2022-08-25
1.2 | project estimation | bar: 2022-07-08 to 2022-07-12; 2022-08-07; 2022-08-22 to 2022-08-25
1.3 | Risk identification | bar: 2022-07-11 to 2022-07-24; 2022-08-07; 2022-08-22 to 2022-08-25
1.4 | project charter | bar: 2022-07-11 to 2022-07-24; 2022-08-07; 2022-08-22 to 2022-08-25
1.5 | risk register | bar: 2022-08-07; 2022-08-22 to 2022-08-25
1.6 | communications plan | bar: 2022-07-04 to 2022-07-10; 2022-08-07; 2022-08-22 to 2022-08-25
1.7 | confirmed requirements list | bar: 2022-07-18 to 2022-07-24; 2022-08-07; 2022-08-22 to 2022-08-25
1.8 | a scope baseline | bar: 2022-07-04 to 2022-07-10; 2022-08-07; 2022-08-22 to 2022-08-25
2 | Communications
2.1 | Team meeting | bar: 2022-06-25; 2022-07-02; 2022-07-13; 2022-07-19; 2022-08-07; 2022-08-22 to 2022-08-25
2.2 | Development Kick-start Meeting | bar: 2022-07-24; 2022-08-07; 2022-08-22 to 2022-08-25
2.3 | Sprint planning | bar: 2022-08-07; 2022-08-22 to 2022-08-25
2.4 | Sprint meeting | bar: 2022-07-31; 2022-08-07; 2022-08-14; 2022-08-21 to 2022-08-25; 2022-08-28
2.5 | Development review meeting | bar: 2022-08-07; 2022-08-22 to 2022-08-25; 2022-08-28; 2022-09-04
3 | Requirements Analysis
3.1 | Review requirements | bar: 2022-08-07; 2022-08-22 to 2022-08-25
3.2 | Convert requirements to user stories | bar: 2022-07-18 to 2022-07-24; 2022-08-07; 2022-08-22 to 2022-08-25
3.3 | Vote Story points to each story | bar: 2022-07-25 to 2022-07-31; 2022-08-07; 2022-08-22 to 2022-08-25
3.4 | Story prioritization | bar: 2022-07-24 to 2022-07-26; 2022-07-31; 2022-08-07; 2022-08-14; 2022-08-21 to 2022-08-25
3.5 | Review if the development match the requirement | bar: 2022-08-01 to 2022-08-27
4 | Toy design / development
4.1 | Discuss / decise game type | bar: 2022-07-04 to 2022-07-10; 2022-08-07; 2022-08-22 to 2022-08-25
4.2 | Game design (without coding) | bar: 2022-07-11 to 2022-07-24; 2022-08-07; 2022-08-22 to 2022-08-25
4.3 | Set up GitHub as repository | bar: 2022-07-25 to 2022-07-31; 2022-08-07; 2022-08-22 to 2022-08-25
4.4 | Graphical interface | bar: 2022-08-01 to 2022-08-14; 2022-08-22 to 2022-08-25
5 | Planned Stories
5.1 | Research for suitable libraries | bar: 2022-07-27 to 2022-07-31; 2022-08-07; 2022-08-22 to 2022-08-25
5.2 | Develop the game mechanics – lucky draw part | bar: 2022-08-22 to 2022-08-25
5.3 | Develop the game mechanics – determine result part | bar: 2022-08-08 to 2022-08-14; 2022-08-22 to 2022-08-25
5.4 | Develop multi-input source support | bar: 2022-08-15 to 2022-08-25
5.5 | Add indicator sound | bar: 2022-08-22 to 2022-08-25
5.6 | Build the graphical interface | bar: 2022-08-07 to 2022-08-14; 2022-08-22 to 2022-08-25
5.7 | Set up database for data storage | bar: 2022-08-07; 2022-08-15 to 2022-08-25
5.8 | Build setting for sound control on/off | bar: 2022-08-07; 2022-08-22 to 2022-08-25
5.9 | Build parent control feature | bar: 2022-08-07; 2022-08-15 to 2022-08-25
5.1o | Develop multilingual support | bar: 2022-08-07; 2022-08-22 to 2022-08-25
5.11 | Preparation for code demonstration and presentation | bar: 2022-08-07
6 | Code Review Demo preparation
6.1 | Discuss / review Demo requirements | bar: 2022-08-07; 2022-08-15 to 2022-08-25
6.2 | Decide the method to deliver the demonstration | bar: 2022-08-07; 2022-08-22 to 2022-08-25
6.3 | Final testing of the game output | bar: 2022-08-07; 2022-08-22 to 2022-08-27
6.4 | Mock-up demo | bar: 2022-08-07; 2022-08-22 to 2022-08-26
6.5 | Record the demo | bar: 2022-08-07; 2022-08-22 to 2022-08-25; 2022-08-28
7 | Presentation preparation
7.1 | Discuss / review presentation requirements | bar: 2022-08-07 to 2022-08-18; 2022-08-22 to 2022-08-25
7.2 | Decide the method to deliver the presentation | bar: 2022-08-07; 2022-08-19 to 2022-08-25
7.3 | PowerPoint Slide | bar: 2022-08-07 to 2022-08-26
7.4 | Complie evidence of project management process | bar: 2022-08-07
7.5 | Mock-up presentation | bar: 2022-08-07; 2022-08-22 to 2022-08-26
7.6 | Record the presentation | bar: 2022-08-07; 2022-08-22 to 2022-08-25; 2022-08-28
8 | Development and execution phase
6.5 | Work towards UAT | bar: 2022-08-07; 2022-08-22 to 2022-08-25; 2022-08-29 to 2022-12-04
8.1 | Launch of UAT | bar: 2022-08-07; 2022-08-22 to 2022-08-25; 2022-12-05 to 2022-12-11
`
Sprint 1 review
Sprint 2 review
Sprint 3 review
Sprint 4 review
Sprint 5 review
Record Demo
Record Presentation
Launch of UAT